## Metric
| Week | MTD (month to date) | Month | Year to date
| May 18 - 24, 2026 | May 1 - 24, 2026 | May 1 - 31, 2026 | 2026
Budget m | 420 | 1440 | 1860 | 2010
Actual m | 571.3 | 1891.8 | 2711.8 | 1891.8

## Imperial
| Week | MTD (month to date) | Month | Year to date
| May 18 - 24, 2026 | May 1 - 24, 2026 | May 1 - 31, 2026 | 2026
Budget ft | 1378 | 4724.4 | 6102.4 | 6594.5
Actual ft | 1874.3 | 6206.7 | 8897 | 6206.7

## Budget Audit
Budget Calculations
Project | Silver Creek
Period | Start | End
Week | 2026-05-18 | 2026-05-24
MTD | 2026-05-01 | 2026-05-24
Month | 2026-05-01 | 2026-05-31
Year to date | 2026-01-01 | 2026-05-24
Assumption | 2 shifts/day x 15 m/shift = 30 m per active rig-day
Period | Date | Rig | Shifts | m/shift | Budget m | Running total m
Week | 2026-05-18 | Rig 12 | 2 | 15 | 30 | 30
Week | 2026-05-18 | Rig 18 | 2 | 15 | 30 | 60
Week | 2026-05-19 | Rig 12 | 2 | 15 | 30 | 90
Week | 2026-05-19 | Rig 18 | 2 | 15 | 30 | 120
Week | 2026-05-20 | Rig 12 | 2 | 15 | 30 | 150
Week | 2026-05-20 | Rig 18 | 2 | 15 | 30 | 180
Week | 2026-05-21 | Rig 12 | 2 | 15 | 30 | 210
Week | 2026-05-21 | Rig 18 | 2 | 15 | 30 | 240
Week | 2026-05-22 | Rig 12 | 2 | 15 | 30 | 270
Week | 2026-05-22 | Rig 18 | 2 | 15 | 30 | 300
Week | 2026-05-23 | Rig 12 | 2 | 15 | 30 | 330
Week | 2026-05-23 | Rig 18 | 2 | 15 | 30 | 360
Week | 2026-05-24 | Rig 12 | 2 | 15 | 30 | 390
Week | 2026-05-24 | Rig 18 | 2 | 15 | 30 | 420
MTD | 2026-05-01 | Rig 12 | 2 | 15 | 30 | 30
MTD | 2026-05-01 | Rig 18 | 2 | 15 | 30 | 60
MTD | 2026-05-02 | Rig 12 | 2 | 15 | 30 | 90
MTD | 2026-05-02 | Rig 18 | 2 | 15 | 30 | 120
MTD | 2026-05-03 | Rig 12 | 2 | 15 | 30 | 150
MTD | 2026-05-03 | Rig 18 | 2 | 15 | 30 | 180
MTD | 2026-05-04 | Rig 12 | 2 | 15 | 30 | 210
MTD | 2026-05-04 | Rig 18 | 2 | 15 | 30 | 240
MTD | 2026-05-05 | Rig 12 | 2 | 15 | 30 | 270
MTD | 2026-05-05 | Rig 18 | 2 | 15 | 30 | 300
MTD | 2026-05-06 | Rig 12 | 2 | 15 | 30 | 330
MTD | 2026-05-06 | Rig 18 | 2 | 15 | 30 | 360
MTD | 2026-05-07 | Rig 12 | 2 | 15 | 30 | 390
MTD | 2026-05-07 | Rig 18 | 2 | 15 | 30 | 420
MTD | 2026-05-08 | Rig 12 | 2 | 15 | 30 | 450
MTD | 2026-05-08 | Rig 18 | 2 | 15 | 30 | 480
MTD | 2026-05-09 | Rig 12 | 2 | 15 | 30 | 510
MTD | 2026-05-09 | Rig 18 | 2 | 15 | 30 | 540
MTD | 2026-05-10 | Rig 12 | 2 | 15 | 30 | 570
MTD | 2026-05-10 | Rig 18 | 2 | 15 | 30 | 600
MTD | 2026-05-11 | Rig 12 | 2 | 15 | 30 | 630
MTD | 2026-05-11 | Rig 18 | 2 | 15 | 30 | 660
MTD | 2026-05-12 | Rig 12 | 2 | 15 | 30 | 690
MTD | 2026-05-12 | Rig 18 | 2 | 15 | 30 | 720
MTD | 2026-05-13 | Rig 12 | 2 | 15 | 30 | 750
MTD | 2026-05-13 | Rig 18 | 2 | 15 | 30 | 780
MTD | 2026-05-14 | Rig 12 | 2 | 15 | 30 | 810
MTD | 2026-05-14 | Rig 18 | 2 | 15 | 30 | 840
MTD | 2026-05-15 | Rig 12 | 2 | 15 | 30 | 870
MTD | 2026-05-15 | Rig 18 | 2 | 15 | 30 | 900
MTD | 2026-05-16 | Rig 12 | 2 | 15 | 30 | 930
MTD | 2026-05-16 | Rig 18 | 2 | 15 | 30 | 960
MTD | 2026-05-17 | Rig 12 | 2 | 15 | 30 | 990
MTD | 2026-05-17 | Rig 18 | 2 | 15 | 30 | 1020
MTD | 2026-05-18 | Rig 12 | 2 | 15 | 30 | 1050
MTD | 2026-05-18 | Rig 18 | 2 | 15 | 30 | 1080
MTD | 2026-05-19 | Rig 12 | 2 | 15 | 30 | 1110
MTD | 2026-05-19 | Rig 18 | 2 | 15 | 30 | 1140
MTD | 2026-05-20 | Rig 12 | 2 | 15 | 30 | 1170
MTD | 2026-05-20 | Rig 18 | 2 | 15 | 30 | 1200
MTD | 2026-05-21 | Rig 12 | 2 | 15 | 30 | 1230
MTD | 2026-05-21 | Rig 18 | 2 | 15 | 30 | 1260
MTD | 2026-05-22 | Rig 12 | 2 | 15 | 30 | 1290
MTD | 2026-05-22 | Rig 18 | 2 | 15 | 30 | 1320
MTD | 2026-05-23 | Rig 12 | 2 | 15 | 30 | 1350
MTD | 2026-05-23 | Rig 18 | 2 | 15 | 30 | 1380
MTD | 2026-05-24 | Rig 12 | 2 | 15 | 30 | 1410
MTD | 2026-05-24 | Rig 18 | 2 | 15 | 30 | 1440
Month | 2026-05-01 | Rig 12 | 2 | 15 | 30 | 30
Month | 2026-05-01 | Rig 18 | 2 | 15 | 30 | 60
Month | 2026-05-02 | Rig 12 | 2 | 15 | 30 | 90
Month | 2026-05-02 | Rig 18 | 2 | 15 | 30 | 120
Month | 2026-05-03 | Rig 12 | 2 | 15 | 30 | 150
Month | 2026-05-03 | Rig 18 | 2 | 15 | 30 | 180
Month | 2026-05-04 | Rig 12 | 2 | 15 | 30 | 210
Month | 2026-05-04 | Rig 18 | 2 | 15 | 30 | 240
Month | 2026-05-05 | Rig 12 | 2 | 15 | 30 | 270
Month | 2026-05-05 | Rig 18 | 2 | 15 | 30 | 300
Month | 2026-05-06 | Rig 12 | 2 | 15 | 30 | 330
Month | 2026-05-06 | Rig 18 | 2 | 15 | 30 | 360
Month | 2026-05-07 | Rig 12 | 2 | 15 | 30 | 390
Month | 2026-05-07 | Rig 18 | 2 | 15 | 30 | 420
Month | 2026-05-08 | Rig 12 | 2 | 15 | 30 | 450
Month | 2026-05-08 | Rig 18 | 2 | 15 | 30 | 480
Month | 2026-05-09 | Rig 12 | 2 | 15 | 30 | 510
Month | 2026-05-09 | Rig 18 | 2 | 15 | 30 | 540
Month | 2026-05-10 | Rig 12 | 2 | 15 | 30 | 570
Month | 2026-05-10 | Rig 18 | 2 | 15 | 30 | 600
Month | 2026-05-11 | Rig 12 | 2 | 15 | 30 | 630
Month | 2026-05-11 | Rig 18 | 2 | 15 | 30 | 660
Month | 2026-05-12 | Rig 12 | 2 | 15 | 30 | 690
Month | 2026-05-12 | Rig 18 | 2 | 15 | 30 | 720
Month | 2026-05-13 | Rig 12 | 2 | 15 | 30 | 750
Month | 2026-05-13 | Rig 18 | 2 | 15 | 30 | 780
Month | 2026-05-14 | Rig 12 | 2 | 15 | 30 | 810
Month | 2026-05-14 | Rig 18 | 2 | 15 | 30 | 840
Month | 2026-05-15 | Rig 12 | 2 | 15 | 30 | 870
Month | 2026-05-15 | Rig 18 | 2 | 15 | 30 | 900
Month | 2026-05-16 | Rig 12 | 2 | 15 | 30 | 930
Month | 2026-05-16 | Rig 18 | 2 | 15 | 30 | 960
Month | 2026-05-17 | Rig 12 | 2 | 15 | 30 | 990
Month | 2026-05-17 | Rig 18 | 2 | 15 | 30 | 1020
Month | 2026-05-18 | Rig 12 | 2 | 15 | 30 | 1050
Month | 2026-05-18 | Rig 18 | 2 | 15 | 30 | 1080
Month | 2026-05-19 | Rig 12 | 2 | 15 | 30 | 1110
Month | 2026-05-19 | Rig 18 | 2 | 15 | 30 | 1140
Month | 2026-05-20 | Rig 12 | 2 | 15 | 30 | 1170
Month | 2026-05-20 | Rig 18 | 2 | 15 | 30 | 1200
Month | 2026-05-21 | Rig 12 | 2 | 15 | 30 | 1230
Month | 2026-05-21 | Rig 18 | 2 | 15 | 30 | 1260
Month | 2026-05-22 | Rig 12 | 2 | 15 | 30 | 1290
Month | 2026-05-22 | Rig 18 | 2 | 15 | 30 | 1320
Month | 2026-05-23 | Rig 12 | 2 | 15 | 30 | 1350
Month | 2026-05-23 | Rig 18 | 2 | 15 | 30 | 1380
Month | 2026-05-24 | Rig 12 | 2 | 15 | 30 | 1410
Month | 2026-05-24 | Rig 18 | 2 | 15 | 30 | 1440
Month | 2026-05-25 | Rig 12 | 2 | 15 | 30 | 1470
Month | 2026-05-25 | Rig 18 | 2 | 15 | 30 | 1500
Month | 2026-05-26 | Rig 12 | 2 | 15 | 30 | 1530
Month | 2026-05-26 | Rig 18 | 2 | 15 | 30 | 1560
Month | 2026-05-27 | Rig 12 | 2 | 15 | 30 | 1590
Month | 2026-05-27 | Rig 18 | 2 | 15 | 30 | 1620
Month | 2026-05-28 | Rig 12 | 2 | 15 | 30 | 1650
Month | 2026-05-28 | Rig 18 | 2 | 15 | 30 | 1680
Month | 2026-05-29 | Rig 12 | 2 | 15 | 30 | 1710
Month | 2026-05-29 | Rig 18 | 2 | 15 | 30 | 1740
Month | 2026-05-30 | Rig 12 | 2 | 15 | 30 | 1770
Month | 2026-05-30 | Rig 18 | 2 | 15 | 30 | 1800
Month | 2026-05-31 | Rig 12 | 2 | 15 | 30 | 1830
Month | 2026-05-31 | Rig 18 | 2 | 15 | 30 | 1860
Year to date | 2026-04-15 | Rig 12 | 2 | 15 | 30 | 30
Year to date | 2026-04-16 | Rig 12 | 2 | 15 | 30 | 60
Year to date | 2026-04-17 | Rig 12 | 2 | 15 | 30 | 90
Year to date | 2026-04-18 | Rig 12 | 2 | 15 | 30 | 120
Year to date | 2026-04-19 | Rig 12 | 2 | 15 | 30 | 150
Year to date | 2026-04-20 | Rig 12 | 2 | 15 | 30 | 180
Year to date | 2026-04-21 | Rig 12 | 2 | 15 | 30 | 210
Year to date | 2026-04-22 | Rig 12 | 2 | 15 | 30 | 240
Year to date | 2026-04-23 | Rig 12 | 2 | 15 | 30 | 270
Year to date | 2026-04-24 | Rig 12 | 2 | 15 | 30 | 300
Year to date | 2026-04-25 | Rig 12 | 2 | 15 | 30 | 330
Year to date | 2026-04-26 | Rig 12 | 2 | 15 | 30 | 360
Year to date | 2026-04-27 | Rig 12 | 2 | 15 | 30 | 390
Year to date | 2026-04-28 | Rig 12 | 2 | 15 | 30 | 420
Year to date | 2026-04-28 | Rig 18 | 2 | 15 | 30 | 450
Year to date | 2026-04-29 | Rig 12 | 2 | 15 | 30 | 480
Year to date | 2026-04-29 | Rig 18 | 2 | 15 | 30 | 510
Year to date | 2026-04-30 | Rig 12 | 2 | 15 | 30 | 540
Year to date | 2026-04-30 | Rig 18 | 2 | 15 | 30 | 570
Year to date | 2026-05-01 | Rig 12 | 2 | 15 | 30 | 600
Year to date | 2026-05-01 | Rig 18 | 2 | 15 | 30 | 630
Year to date | 2026-05-02 | Rig 12 | 2 | 15 | 30 | 660
Year to date | 2026-05-02 | Rig 18 | 2 | 15 | 30 | 690
Year to date | 2026-05-03 | Rig 12 | 2 | 15 | 30 | 720
Year to date | 2026-05-03 | Rig 18 | 2 | 15 | 30 | 750
Year to date | 2026-05-04 | Rig 12 | 2 | 15 | 30 | 780
Year to date | 2026-05-04 | Rig 18 | 2 | 15 | 30 | 810
Year to date | 2026-05-05 | Rig 12 | 2 | 15 | 30 | 840
Year to date | 2026-05-05 | Rig 18 | 2 | 15 | 30 | 870
Year to date | 2026-05-06 | Rig 12 | 2 | 15 | 30 | 900
Year to date | 2026-05-06 | Rig 18 | 2 | 15 | 30 | 930
Year to date | 2026-05-07 | Rig 12 | 2 | 15 | 30 | 960
Year to date | 2026-05-07 | Rig 18 | 2 | 15 | 30 | 990
Year to date | 2026-05-08 | Rig 12 | 2 | 15 | 30 | 1020
Year to date | 2026-05-08 | Rig 18 | 2 | 15 | 30 | 1050
Year to date | 2026-05-09 | Rig 12 | 2 | 15 | 30 | 1080
Year to date | 2026-05-09 | Rig 18 | 2 | 15 | 30 | 1110
Year to date | 2026-05-10 | Rig 12 | 2 | 15 | 30 | 1140
Year to date | 2026-05-10 | Rig 18 | 2 | 15 | 30 | 1170
Year to date | 2026-05-11 | Rig 12 | 2 | 15 | 30 | 1200
Year to date | 2026-05-11 | Rig 18 | 2 | 15 | 30 | 1230
Year to date | 2026-05-12 | Rig 12 | 2 | 15 | 30 | 1260
Year to date | 2026-05-12 | Rig 18 | 2 | 15 | 30 | 1290
Year to date | 2026-05-13 | Rig 12 | 2 | 15 | 30 | 1320
Year to date | 2026-05-13 | Rig 18 | 2 | 15 | 30 | 1350
Year to date | 2026-05-14 | Rig 12 | 2 | 15 | 30 | 1380
Year to date | 2026-05-14 | Rig 18 | 2 | 15 | 30 | 1410
Year to date | 2026-05-15 | Rig 12 | 2 | 15 | 30 | 1440
Year to date | 2026-05-15 | Rig 18 | 2 | 15 | 30 | 1470
Year to date | 2026-05-16 | Rig 12 | 2 | 15 | 30 | 1500
Year to date | 2026-05-16 | Rig 18 | 2 | 15 | 30 | 1530
Year to date | 2026-05-17 | Rig 12 | 2 | 15 | 30 | 1560
Year to date | 2026-05-17 | Rig 18 | 2 | 15 | 30 | 1590
Year to date | 2026-05-18 | Rig 12 | 2 | 15 | 30 | 1620
Year to date | 2026-05-18 | Rig 18 | 2 | 15 | 30 | 1650
Year to date | 2026-05-19 | Rig 12 | 2 | 15 | 30 | 1680
Year to date | 2026-05-19 | Rig 18 | 2 | 15 | 30 | 1710
Year to date | 2026-05-20 | Rig 12 | 2 | 15 | 30 | 1740
Year to date | 2026-05-20 | Rig 18 | 2 | 15 | 30 | 1770
Year to date | 2026-05-21 | Rig 12 | 2 | 15 | 30 | 1800
Year to date | 2026-05-21 | Rig 18 | 2 | 15 | 30 | 1830
Year to date | 2026-05-22 | Rig 12 | 2 | 15 | 30 | 1860
Year to date | 2026-05-22 | Rig 18 | 2 | 15 | 30 | 1890
Year to date | 2026-05-23 | Rig 12 | 2 | 15 | 30 | 1920
Year to date | 2026-05-23 | Rig 18 | 2 | 15 | 30 | 1950
Year to date | 2026-05-24 | Rig 12 | 2 | 15 | 30 | 1980
Year to date | 2026-05-24 | Rig 18 | 2 | 15 | 30 | 2010

## Actual Audit
Actual Depth Calculations
Project | Silver Creek
Period | Start | End
Week | 2026-05-18 | 2026-05-24
MTD | 2026-05-01 | 2026-05-24
Month | 2026-05-01 | 2026-05-31
Year to date | 2026-01-01 | 2026-05-24
Period | Date | Time | Drillhole | Rig | Previous depth m | Depth m | Delta m | Running total m | Update note
MTD | 2026-05-10 | 6:00 PM | NR-26-101 | Rig 12 | 0 | 628.4 | 628.4 | 628.4 | Depth and status update from synthetic field data.
Month | 2026-05-10 | 6:00 PM | NR-26-101 | Rig 12 | 0 | 628.4 | 628.4 | 628.4 | Depth and status update from synthetic field data.
Year to date | 2026-05-10 | 6:00 PM | NR-26-101 | Rig 12 | 0 | 628.4 | 628.4 | 628.4 | Depth and status update from synthetic field data.
MTD | 2026-05-17 | 6:00 PM | NR-26-102 | Rig 12 | 0 | 692.1 | 692.1 | 1320.5 | Depth and status update from synthetic field data.
Month | 2026-05-17 | 6:00 PM | NR-26-102 | Rig 12 | 0 | 692.1 | 692.1 | 1320.5 | Depth and status update from synthetic field data.
Year to date | 2026-05-17 | 6:00 PM | NR-26-102 | Rig 12 | 0 | 692.1 | 692.1 | 1320.5 | Depth and status update from synthetic field data.
Week | 2026-05-23 | 6:00 PM | SC-26-103 | Rig 18 | 0 | 571.3 | 571.3 | 571.3 | Depth and status update from synthetic field data.
MTD | 2026-05-23 | 6:00 PM | SC-26-103 | Rig 18 | 0 | 571.3 | 571.3 | 1891.8 | Depth and status update from synthetic field data.
Month | 2026-05-23 | 6:00 PM | SC-26-103 | Rig 18 | 0 | 571.3 | 571.3 | 1891.8 | Depth and status update from synthetic field data.
Year to date | 2026-05-23 | 6:00 PM | SC-26-103 | Rig 18 | 0 | 571.3 | 571.3 | 1891.8 | Depth and status update from synthetic field data.
Month | 2026-05-30 | 6:00 PM | SC-26-104 | Rig 18 | 0 | 436 | 436 | 2327.8 | Depth and status update from synthetic field data.
Month | 2026-05-30 | 6:00 PM | NR-26-105 | Rig 12 | 0 | 384 | 384 | 2711.8 | Depth and status update from synthetic field data.

## Active Days
Active Rig-Day Tally
Project | Silver Creek
Period | Start | End
Week | 2026-05-18 | 2026-05-24
MTD | 2026-05-01 | 2026-05-24
Month | 2026-05-01 | 2026-05-31
Year to date | 2026-01-01 | 2026-05-24
Date | Active rig count | Active rigs | Budget m | Week | MTD | Month | Year to date
2026-01-01 | 0 |  | 0 |  |  |  | Y
2026-01-02 | 0 |  | 0 |  |  |  | Y
2026-01-03 | 0 |  | 0 |  |  |  | Y
2026-01-04 | 0 |  | 0 |  |  |  | Y
2026-01-05 | 0 |  | 0 |  |  |  | Y
2026-01-06 | 0 |  | 0 |  |  |  | Y
2026-01-07 | 0 |  | 0 |  |  |  | Y
2026-01-08 | 0 |  | 0 |  |  |  | Y
2026-01-09 | 0 |  | 0 |  |  |  | Y
2026-01-10 | 0 |  | 0 |  |  |  | Y
2026-01-11 | 0 |  | 0 |  |  |  | Y
2026-01-12 | 0 |  | 0 |  |  |  | Y
2026-01-13 | 0 |  | 0 |  |  |  | Y
2026-01-14 | 0 |  | 0 |  |  |  | Y
2026-01-15 | 0 |  | 0 |  |  |  | Y
2026-01-16 | 0 |  | 0 |  |  |  | Y
2026-01-17 | 0 |  | 0 |  |  |  | Y
2026-01-18 | 0 |  | 0 |  |  |  | Y
2026-01-19 | 0 |  | 0 |  |  |  | Y
2026-01-20 | 0 |  | 0 |  |  |  | Y
2026-01-21 | 0 |  | 0 |  |  |  | Y
2026-01-22 | 0 |  | 0 |  |  |  | Y
2026-01-23 | 0 |  | 0 |  |  |  | Y
2026-01-24 | 0 |  | 0 |  |  |  | Y
2026-01-25 | 0 |  | 0 |  |  |  | Y
2026-01-26 | 0 |  | 0 |  |  |  | Y
2026-01-27 | 0 |  | 0 |  |  |  | Y
2026-01-28 | 0 |  | 0 |  |  |  | Y
2026-01-29 | 0 |  | 0 |  |  |  | Y
2026-01-30 | 0 |  | 0 |  |  |  | Y
2026-01-31 | 0 |  | 0 |  |  |  | Y
2026-02-01 | 0 |  | 0 |  |  |  | Y
2026-02-02 | 0 |  | 0 |  |  |  | Y
2026-02-03 | 0 |  | 0 |  |  |  | Y
2026-02-04 | 0 |  | 0 |  |  |  | Y
2026-02-05 | 0 |  | 0 |  |  |  | Y
2026-02-06 | 0 |  | 0 |  |  |  | Y
2026-02-07 | 0 |  | 0 |  |  |  | Y
2026-02-08 | 0 |  | 0 |  |  |  | Y
2026-02-09 | 0 |  | 0 |  |  |  | Y
2026-02-10 | 0 |  | 0 |  |  |  | Y
2026-02-11 | 0 |  | 0 |  |  |  | Y
2026-02-12 | 0 |  | 0 |  |  |  | Y
2026-02-13 | 0 |  | 0 |  |  |  | Y
2026-02-14 | 0 |  | 0 |  |  |  | Y
2026-02-15 | 0 |  | 0 |  |  |  | Y
2026-02-16 | 0 |  | 0 |  |  |  | Y
2026-02-17 | 0 |  | 0 |  |  |  | Y
2026-02-18 | 0 |  | 0 |  |  |  | Y
2026-02-19 | 0 |  | 0 |  |  |  | Y
2026-02-20 | 0 |  | 0 |  |  |  | Y
2026-02-21 | 0 |  | 0 |  |  |  | Y
2026-02-22 | 0 |  | 0 |  |  |  | Y
2026-02-23 | 0 |  | 0 |  |  |  | Y
2026-02-24 | 0 |  | 0 |  |  |  | Y
2026-02-25 | 0 |  | 0 |  |  |  | Y
2026-02-26 | 0 |  | 0 |  |  |  | Y
2026-02-27 | 0 |  | 0 |  |  |  | Y
2026-02-28 | 0 |  | 0 |  |  |  | Y
2026-03-01 | 0 |  | 0 |  |  |  | Y
2026-03-02 | 0 |  | 0 |  |  |  | Y
2026-03-03 | 0 |  | 0 |  |  |  | Y
2026-03-04 | 0 |  | 0 |  |  |  | Y
2026-03-05 | 0 |  | 0 |  |  |  | Y
2026-03-06 | 0 |  | 0 |  |  |  | Y
2026-03-07 | 0 |  | 0 |  |  |  | Y
2026-03-08 | 0 |  | 0 |  |  |  | Y
2026-03-09 | 0 |  | 0 |  |  |  | Y
2026-03-10 | 0 |  | 0 |  |  |  | Y
2026-03-11 | 0 |  | 0 |  |  |  | Y
2026-03-12 | 0 |  | 0 |  |  |  | Y
2026-03-13 | 0 |  | 0 |  |  |  | Y
2026-03-14 | 0 |  | 0 |  |  |  | Y
2026-03-15 | 0 |  | 0 |  |  |  | Y
2026-03-16 | 0 |  | 0 |  |  |  | Y
2026-03-17 | 0 |  | 0 |  |  |  | Y
2026-03-18 | 0 |  | 0 |  |  |  | Y
2026-03-19 | 0 |  | 0 |  |  |  | Y
2026-03-20 | 0 |  | 0 |  |  |  | Y
2026-03-21 | 0 |  | 0 |  |  |  | Y
2026-03-22 | 0 |  | 0 |  |  |  | Y
2026-03-23 | 0 |  | 0 |  |  |  | Y
2026-03-24 | 0 |  | 0 |  |  |  | Y
2026-03-25 | 0 |  | 0 |  |  |  | Y
2026-03-26 | 0 |  | 0 |  |  |  | Y
2026-03-27 | 0 |  | 0 |  |  |  | Y
2026-03-28 | 0 |  | 0 |  |  |  | Y
2026-03-29 | 0 |  | 0 |  |  |  | Y
2026-03-30 | 0 |  | 0 |  |  |  | Y
2026-03-31 | 0 |  | 0 |  |  |  | Y
2026-04-01 | 0 |  | 0 |  |  |  | Y
2026-04-02 | 0 |  | 0 |  |  |  | Y
2026-04-03 | 0 |  | 0 |  |  |  | Y
2026-04-04 | 0 |  | 0 |  |  |  | Y
2026-04-05 | 0 |  | 0 |  |  |  | Y
2026-04-06 | 0 |  | 0 |  |  |  | Y
2026-04-07 | 0 |  | 0 |  |  |  | Y
2026-04-08 | 0 |  | 0 |  |  |  | Y
2026-04-09 | 0 |  | 0 |  |  |  | Y
2026-04-10 | 0 |  | 0 |  |  |  | Y
2026-04-11 | 0 |  | 0 |  |  |  | Y
2026-04-12 | 0 |  | 0 |  |  |  | Y
2026-04-13 | 0 |  | 0 |  |  |  | Y
2026-04-14 | 0 |  | 0 |  |  |  | Y
2026-04-15 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-16 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-17 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-18 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-19 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-20 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-21 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-22 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-23 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-24 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-25 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-26 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-27 | 1 | Rig 12 | 30 |  |  |  | Y
2026-04-28 | 2 | Rig 12, Rig 18 | 60 |  |  |  | Y
2026-04-29 | 2 | Rig 12, Rig 18 | 60 |  |  |  | Y
2026-04-30 | 2 | Rig 12, Rig 18 | 60 |  |  |  | Y
2026-05-01 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-02 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-03 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-04 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-05 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-06 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-07 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-08 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-09 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-10 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-11 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-12 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-13 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-14 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-15 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-16 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-17 | 2 | Rig 12, Rig 18 | 60 |  | Y | Y | Y
2026-05-18 | 2 | Rig 12, Rig 18 | 60 | Y | Y | Y | Y
2026-05-19 | 2 | Rig 12, Rig 18 | 60 | Y | Y | Y | Y
2026-05-20 | 2 | Rig 12, Rig 18 | 60 | Y | Y | Y | Y
2026-05-21 | 2 | Rig 12, Rig 18 | 60 | Y | Y | Y | Y
2026-05-22 | 2 | Rig 12, Rig 18 | 60 | Y | Y | Y | Y
2026-05-23 | 2 | Rig 12, Rig 18 | 60 | Y | Y | Y | Y
2026-05-24 | 2 | Rig 12, Rig 18 | 60 | Y | Y | Y | Y
2026-05-25 | 2 | Rig 12, Rig 18 | 60 |  |  | Y
2026-05-26 | 2 | Rig 12, Rig 18 | 60 |  |  | Y
2026-05-27 | 2 | Rig 12, Rig 18 | 60 |  |  | Y
2026-05-28 | 2 | Rig 12, Rig 18 | 60 |  |  | Y
2026-05-29 | 2 | Rig 12, Rig 18 | 60 |  |  | Y
2026-05-30 | 2 | Rig 12, Rig 18 | 60 |  |  | Y
2026-05-31 | 2 | Rig 12, Rig 18 | 60 |  |  | Y